## RACI
Phase (Scope/ Design/ Build/ Test/ Implementation/ Sustain) | Process Level 1 | Process Level 2 | Role | [14 empty] | Input | Output | Comment
|  |  | Global Programme Manager | Commercial | PMO | Engineering Lead | Transformation Leads | Product Mgt | IT Lead | Solution Arch. Lead | IT Commercial Lead | Solution Arch. Commercial | IT Consultant | Delivery Lead | Country IT Lead | IT Solution Lead
Portfolio Board
| Evaluation of project need & objective | Use Case Submission/ Business Case Development (Readiness Roadmap Checklist) |  | R/A | I | C | C/I |  | I |  | C |  |  |  | I |  | I | - Business input - Use Case submission on Hub - Supporting documents (e.g. line status) | - Use Case submission on Hub - Initial functional readiness - triggers for SC analysis and technical assessment
| G0 sign-off (Stage Gate Level 0) | G0 preparation | [16 empty] | - stage gate template for sign-off
| G0 sign-off (Stage Gate Level 0) | LT sign-off | [16 empty] | - official LT sign off (communication post meeting)
| G0 sign-off (Stage Gate Level 0) | G0 approval/ prioitization & sign-off | [16 empty] | Official sign-off - Portfolio Board G0 approval - Benefits hierarchy (Level 1 &2)

## Explanation RACI
Explanation RACI
R | Responsible | person who performs an activity or does the work
A | Accountable | person who is ultimately accountable and has Yes/No/Veto
C | Contributor | person that needs to feedback and contribute to the activity
I | Informed | person that needs to know of the decision or action