## Project RACI
Task | Detailed Activity | MML Projects & Coaching
|  | Business Owner | Prog Mgr | Snr Project Mgrs | Country PM's | TDA | Finance Analyst | Commercial Analyst | Procurement Lead | PMO | Bus' Change Mgr | Training manager | Communication Manager
Requirements Gathering | First Contact & Project Overview & "Target State" | C | A | R | I |  |  |  |  | C
| Confirm Site Scope | C | A | R | I
| HL Requirements Site Overview | C | A | R | C | C |  |  |  | C
| Gather requirements - Min to complete Adv. HW Ordering | C | A | R | C | C
| Full Detailed Completion | I | I | A | R | C
| Trunk Requirements | C | A | R | C | C |  | C
| Requirements Capture |  | C | C | C | C
| Forms | I | I | A | R | R | I
Product Suitability & Capability

## Explanation
Explanation RACI
R | Responsible | person who performs an activity or does the work
A | Accountable | person who is ultimately accountable and has Yes/No/Veto
C | Contributor | person that needs to feedback and contribute to the activity
I | Informed | person that needs to know of the decision or action

## Sheet3 (hidden)
Request
| Raise service Requests/incidents | RA | IC |  |  |  |  | New DDI, Phone, Policy, etc.
| Raise Changes | IC |  | I | RA | RA | C | Firmware patch phones, BT outages/changes, Hardware replacements
| Capture complete Requirements(including features & policies) | C |  | I | I | RA
| License Requirement confirmation (CAP & Intune) |  |  |  |  | RA
New Voice User/Phone Requirement for Exiting User
Confirm if Teams Voice available in the country
Confirm if Phone is required for the user
Assign E5 license
Assign Phone system License
Assign Intune & MFA policies
Assign DDI to Account and Enable Voice Policies
Procure and Install Phone
Phone Enrolment
New CAP/Conference Phone Requirement
Confirm if Teams Voice available in the country
Create CAP AAD Account & Set Password Expiry Policy
Assign Intune & CAP licenses
Assign Intune & MFA policies
Assign DDI to Account and Enable Voice Policies
Procure and Install Phone
Phone Enrolment
Shared Account (Reception/Security)
Confirm if Teams Voice available in the country
Confirm if shared account exists
Assign Phone System Licenses
Assign Intune & MFA policies
Assign DDI to Account and Enable Voice Policies
Procure and Install Phone
Phone Enrolment
Decommission
Remove Voice Allocation
Remove Voice Licenses
Collection/Disposal of Phones
Teams Admin Phone De-enrolment
Delete AAD CAP Account
Change in location for Voice User/Change in Name/Change of Voice Privileges
Reset of Teams Phones(Remotely)
Collection/Disposal of Phone
Removal of local DDI and policies
Assign new DDI and policies
Amend User privileges
Adding/Removing User to Call Queue/AA
Modification to existing Call Queue/AA

## MSTeams Phones RACI-NEW (hidden)
Category | Description | User/GEOIT | Service Desk | Teams (Julie Herbert / Avanade) | M&D Service Owner (Jen Starkey) (Julie Forshaw) | M&D (Solution & Capability) | IDAM (Fiona Richardson) | GTV Team (JM) | BT | SAM Team | Microsoft | Comments | FVT Program Team Comments
Operational Service Management | Create request forms MS Teams Phones | I |  |  | C |  |  | RA |  |  |  | Informed that this is in progress with Jonathan
Operational Service Management | New/Modify/Delete request for MS Teams Phones | RA |  |  | C | I | [5 empty] | Informed that this is in progress with Jonathan
Operational Service Management | Action the MSTeams Phone request (as stated above) | R |  |  | C | I | C | A | A |  |  | This should be as per the process flow suppied by Julian - Is the process of creating SIP, Creating account, applying license etc automated. This should be initiated as part of the ServiceNow request process
Operational Service Management | Installer coordination for demand (if any) | [10 empty] | Is this expected to be 'Self Service' - Are there installation instructions, especially for the CAP phones already produced
Operational Service Management | Procurement of devices | [10 empty] | Is there an established ordering process for telephones? Whos is expected to raise the demand? Will there be a stock of devices held at sites?
Operational Service Management | Raising of DOs for devices | [10 empty] | As above. Are these purchased Ad Hoc
Operational Service Management | Delivery of devices | RA
Operational Service Management | Physical installation of devices on site | [10 empty] | Inside of the project who will perform the installation of the device? Outside of the project who is expected to perform the physical installation of the device? | To be discussed for the BAU phase
Operational Service Management | Physical setup & connectivity | [10 empty] | Device enrolement. Who will perform this? | MDM Team
Operational Service Management | Request Telephone accounts (Teams based) | [10 empty] | Does this get initiated as part of the Service Request? | YES
Operational Service Management | Create Telephone accounts |  |  | R |  |  |  |  | RA
Operational Service Management | Logging of assets - assume CMDB | [10 empty] | Confirmation required if devices will be in CMDB? | NO - Too small a device for inclusion
Technical Solution / Support / Capability | Strategic Roadmap and timelines | I |  | I | C | A |  | R |  |  | C
Technical Solution / Support / Capability | New technology evaluation |  |  | I | RA | R | I | C |  |  |  | Who owns the vendor relationship with YeaLink? Will the be Julie Foreshaw | Global Procurement - Simon Weeks/Sandra
Technical Solution / Support / Capability | Selection of devices and catalogue inclusion | I |  |  | R | RA |  | C |  |  |  | Tany Thomas is the device catalogue owner
Technical Solution / Support / Capability | Testing of devices 'Seed Units' |  |  | I | C | RA |  | C |  |  |  | Tany Thomas is the device catalogue owner
Technical Solution / Support / Capability | Sign-off the Technology choices for MSTeams Phones |  |  | I | RA | R | I | C |  |  |  | Tany Thomas is the device catalogue owner
Technical Solution / Support / Capability | Housekeeping of Device Catalogue | I |  | I | R | RA |  | C |  |  |  | Tany Thomas is the device catalogue owner
Technical Solution / Support / Capability | Comms on catalogue changes | I |  |  | RA | R |  | C |  |  |  | Tany Thomas is the device catalogue owner
Technical Solution / Support / Capability | Configuration & build documentation |  |  |  | C | RA | I | C
Technical Solution / Support / Capability | Technical setup & InfoSec approval |  |  |  | RA | C | I | C |  |  |  | Is this in place for current devices? Were are the information security/EA approvals held | Technical Setup for Yealink Teams Phones is documented. Security Approval is being triggered by Chandni based on the new models of Android v9 phones we are about to procure.
Technical Solution / Support / Capability | Device health management - Firmware Version (Evergreen of device) |  |  | I | RA | CI |  | I |  |  | I | To be confirmed if this is to be performed from within Teams Admin Centre (or YeaLink management platform) SOP Required | MDM Decision. Recommend Teams Admin to simplify device management in a single console - using MS best practice. Infosec best practice for Firmware ? T-1 ? SoP should be as per MDM team standards and applied appropriately.
Technical Solution / Support / Capability | Device health management - OS updates (Evergreen of device) |  |  | I | RA | CI |  | I |  |  | I | To be confirmed if this is to be performed from within Teams Admin Centre (or YeaLink management platform) SOP Required | MDM Decision. Recommend Teams Admin to simplify device management in a single console - using MS best practice. Infosec best practice for Firmware ? T-1 ? SoP should be as per MDM team standards and applied appropriately.
Technical Solution / Support / Capability | Device health management - MS Teams updates (Evergreen of device) |  |  | I | RA | CI |  | I |  |  | I | To be confirmed if this is to be performed from within Teams Admin Centre (or YeaLink management platform) SOP Required | MDM Decision. Recommend Teams Admin to simplify device management in a single console - using MS best practice. Infosec best practice for Firmware ? T-1 ? SoP should be as per MDM team standards and applied appropriately.
MDM | Evaluate Device Management Capability (within InTune and Teams Admin Centre) |  |  | I | I | RA |  | CI |  |  | C | Dave Finan will be looking to achieve full management capability, within InTune and Teams Admin Centre - Yealink will then be assessed to understand the additional capability and pros & cons | No action
MDM | Evaluate Device Management Capability (within YeaLink Management Platform) |  |  |  | I | RA |  | CI |  |  |  | Dave Finan - Is this only required so that you understand what IS possible from within the YeaLink Management Platform. | No action
MDM | Document Technical & Functional Requirements for hardware |  |  |  | I | CI | C | RA |  |  |  | Expect the technical/functional requirements to initially come from the project. | We will share BT policies that are being closed this week which define what each user type can perform on the different phone types. Will be shared with design doc.
MDM | InTune - Create/Test/Implement Policies (Device Compliance Policies) |  |  |  | I | RA |  | C |  |  |  | These define the rules and settings that a device must comply with in order to be considered compliant by conditional access polices. You can also use compliance policies to monitor and remediate the compliance of devices independently of conditional access. | No action. MDM Team own this
MDM | InTune - Create/Test/Implement Policies (Configuration Policies) |  |  |  | I | RA |  | C |  |  |  | Information Security would be consulted Configuration policies: These are commonly used to manage security settings and features on your devices. | No action. MDM Team own this
MDM | InTune - Enrolement testing and refinement of documentation |  |  |  | I | RA |  | C |  |  |  | Dependencies Acct/Groups/Policies/Conditional Access policy/Teams Phone Policy | No action. MDM Team own this
MDM | Build/Develop Conditional Access Policies (IDAM) |  |  |  | I | CI | RA | C |  |  |  | These policies help you secure email and other services depending on conditions you specify. | No action. MDM Team own this
MDM | InTune - BAU Support of Intune Policies |  | I |  |  | RA |  | C |  |  |  | Support model clarification required - Build improvements/remediation etc will go through S&C New hardware/Service Improvements/Feature enhancements | FVT Program will share support model for BAU. This can be used to support the Intune Policies
BAU & Strategic Support | Monitoring of alerts - Incidents (Yealink Management Console) |  |  |  | C | RA |  | I |  |  |  | Discuss | We are not aware of any device monitoring, unless MDM team plan to use Yealink mgmt console. Via CQD we can monitor and report on device call performance only, not Hardware. We can discuss on this subject - cannot see benefit in proactive HW monitoring for small consumable items. Upto MDM team
BAU & Strategic Support | ProActive Resolution - Incidents (Yealink Management Console) |  |  |  | C | RA |  | I |  |  |  | Discuss | We are not aware of any device monitoring, unless MDM team plan to use Yealink mgmt console. Via CQD we can monitor and report on device call performance only, not Hardware. We can discuss on this subject - cannot see benefit in proactive HW monitoring for small consumable items. Upto MDM team
BAU & Strategic Support | Incident is raised with Helpdesk | [10 empty] | Discuss | Part of incident support flow, to be shared and discussed.
BAU & Strategic Support | Create Initial Knowledge Articles for UNA & Service Desk |  | C | R | R |  | R | RA | R | R | C | Are these already created as part of the project transition to service | Being developed in Snow.
BAU & Strategic Support | Level 1 Support | [10 empty] | Is there a full support model for the devices? Do Unisys need to be aware of these devices as they will be enroled into InTune | As per #36. MDM Team need to decide if they wish Unisys to support these. Currently these phones, and the legacy phones were deemed as consumables. GEO will fund and replace if device fails. Intune and software policy management could be guided by MDM team.
BAU & Strategic Support | Level 2 Support | [10 empty] | Is there a full support model for the devices? Do Unisys need to be aware of these devices as they will be enroled into InTune | as above
BAU & Strategic Support | Level 3 Support | [10 empty] | Is there a full support model for the devices? Do Unisys need to be aware of these devices as they will be enroled into InTune | as above
BAU & Strategic Support | Service Management ownership |  |  | I | RA |  |  | C
BAU & Strategic Support | Regular updates to Helpfile | I | I |  | C | RA |  | C |  |  |  |  | MDM Standard policies should apply
Device Lifecycle | Define Break Fix Process / Strategy | [11 empty] | MDM Standard policies should apply
Device Lifecycle | Define Refresh Strategy | I |  |  | C | RA |  | C |  |  |  | Recommended that this sits with M&D (Moises). The device(s) will need to be built into a refresh plan and will need to be included within the M&D RF etc. Device(s) must be held in CMDB so that they can be lifecycle managed | GEO IT will own these devices, so not sure if HW refresh policy applies - unless OS/Firmware falls behind security minimum. Discuss - who will replace and pay for new HW? Catalogue to be kept upto date in accordance with device/OS lifecycle.
Device Lifecycle | Decomission - Hardware Disposal | C |  |  | RA |  |  | I |  |  |  | Does Moises need to be consulted on this? Wipe of devices? And dispoal through an environmentally responsible company | As part of the Decom process for devices, these would need a remote wipe from Teams Admin
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs to be 1 step, the process setup is part of the process document.
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We are not going to put the devices in CMDB.
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need confimation if we are going to use YMC